## Intro
Product Backlog - list of all product features, product owner responsible for prioritizing
Sprint Backlog - the to do list for the sprint
Burndown Chart - chart that shows how much work remains in a sprint
Release Backlog - same as the product backlog, may involve one or more sprints
Estimating:
User Story - high level definition of what the customer wants to do 'As a (user), I want (function) so that (desired result)
Story Points - simple way to estimate a level of effort (relative scoring used - from 1 - 10, with 1 being easy and 10 being most difficult.
Business Value - each user story has in the Product Backlog has a business value assigned - typically H, M, L

## Product Backlog
Product Backlog
Complete the Product Backlog with data for each of the stories (components) of the project. Fields with calculated data are shaded in grey. For definitions of each data component, hover over the title.
Overall Project Estimates
| The data is calculated from the details below |  | Work Estimate for Sprint 1 | 93
|  |  | Work Estimate for Sprint 2 | 31
|  |  | Work Estimate for Sprint 3 | 0
|  |  | Work Estimate for Sprint 4 | 0
|  |  | Work Estimate for Sprint 5 | 0
|  |  | Work Estimate for Sprint 6 | 0
|  |  | Work Estimate for Sprints 7 and beyond | 0
| This data should be completed at the beginning of the current Sprint |  | Total Sprint Information
|  |  | Current Sprint: | 1
|  |  | Total User Story Hours | 93
|  |  | Total available hrs for the sprint: | 120
|  |  | Focus Factor | 77.5%
|  |  | Number of Resources in Sprint | 3
| This data should be updated daily to determine resource requirements to finish the current Sprint |  | Current Sprint In-Progress Details
|  |  | User Stories Hours Remaining | 25
|  |  | Work Hours Remaining | 24 | Assume 8 hours per day
|  |  | Difference: | -1
|  |  | Work Days Remaining in Sprint | 1
|  |  | Number of Days in Sprint | 5
Details | [5 empty] | Team | [6 empty] | Sprint 1 | Sprint 2 | Sprint 3 | Sprint 4 | Sprint 5 | Sprint 6 | Later
Epic | Sprint | User Story Role | User Story Name | Story Details | Acceptance Test Criteria | How to Demo | Tasks | Analyst / Prep work | Development Estimate | QA | Total User Story | Time Remaining
New Art Gallery Website | 1 | Gallery Owner | Create web page for each artist | There are 20 artists currently exhibiting at the gallery. Each artist should be provided 1 page to showcase their art | 1. 20 web pages must be on the website 2. Each artist must be listed on the page with their bio 3. At least one piece of art should be described and a picture included on each page |  | 1. Develop a template for each artist to fill out for each piece of art that is to be displayed on the website. 2. Request bio and picture from each artist 3. Request artist to fill out template of each art piece to be presented on webpage along with at least 1 picture of art piece 3. Update each artists web page with Name, Bio & art pieces requested with pictures. | 5 | 60 | 10 | 75 | 0 | 75 | 0 | 0 | 0 | 0 | 0 | 0
New Art Gallery Website | 1 | Gallery Owner | Create main Gallery Webpage | New gallery wants to build a community between the artists, the gallery & the customers. | 1. The main page of the website should describe the gallery and its mission. 2. The main page of the website should have a link to each of the artist pages that are currently exhibiting at the gallery |  | 1. Define the look and feel of the webpage for the gallery 2. Obtain the content that describes the gallery's mission 3. Determine and implement a way to link to all the artists from the main page simply | 10 | 8 |  | 18 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
New Art Gallery Website | 2 | Gallery Owner | Artist & Customer communication | Customers should be able to chat directly with artists to learn more about any art pieces they may be interested in. | 1. Customers should be able to send a message to the artist. There is no requirement that the artist respond immediately. 2. Artists must have a way to respond to the customer 3. The interaction between artist and customer can be public or private. |  |  | 5 | 24 | 2 | 31 | 0 | 0 | 31 | 0 | 0 | 0 | 0 | 0
Note on E5: Computed from the data entered in the details below.
Note on E13: Enter the sequence number for the Sprint in progress.
Note on E14: This is the total number of hours estimated for this Sprint.
Note on E15: This is the total person hours available for the current Sprint.
Note on E16: This is the ratio of hours required for the sprint to the resource hours assigned. A ratio of greater than 80% provides little contingency for unplanned events. In this case, we suggest shifting some stories to a later Sprint.
Note on E19: Enter hours estimated to complete the Sprint
Note on E20: Enter the number of person-hours remaining on the Sprint
Note on E21: If the number of work hours remaining is less than it will take to finish the project, shiftsome stories to a later Sprint
Note on M26: Andy Woyzbun: This is the total of development estimate and QA estimate

## Sprint Example
Sprint Progress Tracking - An Example
This Tab enables the Scrum Master to track the progress of the Sprint relative to the Plan. Each day, enter the number of hours remaining in the Sprint. The graph compares the planned Sprint completion with the actual progress. The Ideal Line shows the progress that would be expected if the Sprint proceeds as planned. The Time Remaining line shows the actual progress for the Sprint. On any day, if the Time Remaining is above the Ideal Line, the project is running late. If this is a consistent and significant trend for more than two days, defer some stories to a later Sprint and record this change in the Project Information. Use the Blockers table to record non-Sprint activities that affected the Sprint. These should be used to improve estimates for later Sprints.
Enter Sprint Number | 2 |  | This example uses different data than that in the Product Backlog Example
Day of the Sprint - assumes 10 day sprints | Enter Total Hours Remaining | Ideal Line
0 | 126 | 126
1 | 115
2 | 115
3 | 115
4 | 98.2
5 | 92.6
6 | 90.6
7 | 14
8 | 14
9 | 0
10 | 0 | 0
Blockers | Hours Spent
Data Base | 8
Prod Issue
Meetings | 12
Sick
Slush | 3
Bug
TOTAL | 23